## Form
County: |  |  |  | Project Name:
Project ID#/ Contract #: |  |  |  | Contract Start Date: |  | Contract End Date:
Current Report Date: |  |  |  | SWCD Employee Name/Title:
[5 empty] | SWBP Plan of Work (To be completed and submitted with Application documents) | SWBP Interim Report (To be submitted with each Claim for Payment request for Interim Payments 1, 2, and Final Payment)
Landowner First Name | Landowner Last Name | Project Deliverables | Tasks to be Performed | Name(s) of Personnel Performing Tasks | Proposed Completion Date | Actual Date of Completion
|  | Preliminary Approval of Project (To be completed after contract execution to 18 months) | Certification of Title Curatives and a) copies of any attachments referenced in the certification, b) a copy of title insurance commitment, including a legible copy of each document listed in its Schedule A, c) copies of all proposed curatives
Boundary survey of the easement area
DRAFT Conservation Easement
Site Plan
|  | Project File (To be completed 18 months to 2 years) | Final DRAFT Conservation Easement
Copy of recorded Conservation Easement
Proof of Conservation Easement conveyance
|  | BMP Implementation (If applicable, to be completed after conservation easement execution) | BMP Survey and Design
BMP Implementation, Construction Inspection
BMP Certification
Contract Administration
Financial Status of the Project
Funds Expended this reporting period (Yes/No)? |  |  | Notes - Problems encountered, additional Information related to progress on the deliverables, etc.
Budget report form attached (Yes/No)?
Claim for Payment submitted (Yes/No)?

## Instructions
Instructions for filling out SWBP Plan of Work (SW-5)
Preliminary Approval Definintions
- Certification of Title Curatives: this certifies a clear title and shall be provided by the Grantee's attorney.
- Draft Conservation Easement: A "red-lined" version of the Department's conservation easement is a digital file which had "track changes" feature turned on before any modification was made to the original digital file. The "red-lined" version shall reveal all modifications made to the easement document.
- Site Plan: A map that shows the project area for each participating farm. Submit only if a modification has been made to the project area that was represented in the grant application.
Project File Definitions
- Final Draft Conservation Easement: A final version of the Draft conservation easement that has received the Department's preliminary approval.
- Copy of recorded conservation easement: a copy of the final easement, showing it has been recorded in the public records
- Proof Conservation Easement conveyance: written proof that the easement has been conveyed (i.e., copy of easement signature page, written letter from Grantor, etc.)

## Sheet1
Access Control System | BMP Survey and Design | Yes
Agrichemical Handling and Storage System | BMP Implementation, Construction Inspection | No
Composting System - Animal | BMP Certification
Erosion Control System - Structural | AEM Tier 3 Plan Development
Feed Management System | AEM Tier 3 Plan Certification
Integrated Pest Management System | Contract Administration
Irrigation Water Management System
Livestock Heavy Use Area Runoff Management System
Manure and Agricultural Waste Treatment System | BMP Survey and Design
Nutrient Management System - Cultural | BMP Implementation, Construction Inspection
Pathogen Management System | BMP Certification
Petroleum and Oil Products Storage System
Prescribed Rotational Grazing System
Process Wash Water Management System
Riparian Buffer System
Silage Leachate Control and Treatment System
Soil Conservation System - Cultural
Stream Corridor and Shoreline Management System
Waste Storage and Transfer System
Tier 3B Plan